## Read Me
PROJECT 06 — CLIENT ONBOARDING & ADMIN WORKFLOW SYSTEM
Portfolio Sample ¦ Fictional Business Scenario: Northstar Creative Co.
Purpose | Demonstrate how a Documentation & Administrative VA can organize a new-client onboarding process from signed agreement to fully onboarded.
Workflow | New Client → Information → Documents → File Setup → Welcome → Initial Tasks → Follow-up → Fully Onboarded
Workbook Contents | Onboarding Tracker • Onboarding Checklist • Client Information • Document Checklist • Dashboard • Email Templates
Skills Demonstrated | Administrative Support • Documentation • File Management • Task Coordination • Follow-ups • Workflow Organization • Client Communication
Portfolio Note | Fictional sample created to demonstrate capabilities; not presented as client work.

## Dashboard
CLIENT ONBOARDING DASHBOARD
Quick view of active onboarding workload
TOTAL CLIENTS |  | COMPLETED | IN PROGRESS | WAITING
URGENT |  | HIGH PRIORITY | PENDING ACTIONS | COMPLETION RATE
ONBOARDING STATUS
Status | Count
Not Started
In Progress
Waiting
Completed
On Hold

## Lists & Controls (hidden)
Status | Priority | Client Type | Document Status | Task Category | Owner
Not Started | Low | Service Business | Not Requested | Information | Admin VA
In Progress | Normal | E-commerce | Requested | Documents | Business Owner
Waiting | High | Consultant | Received | Files | Client
Completed | Urgent | Agency | Verified | Communication
On Hold |  | Other | Not Applicable | Setup
Follow-up

## Onboarding Tracker
CLIENT ONBOARDING TRACKER
Centralized view of client onboarding progress
Client ID | Client / Business | Client Type | Start Date | Target Completion | Priority | Onboarding Stage | Status | Owner | Next Action | Follow-up Date | Notes
CL-001 | BrightPath Consulting | Consultant | 2026-09-01 | 2026-09-05 | High | Documents | In Progress | Admin VA | Verify service agreement and ID documents. | 2026-09-05 | Two documents received; one pending.
CL-002 | Luna Home Studio | E-commerce | 2026-09-02 | 2026-09-06 | Normal | File Setup | In Progress | Admin VA | Create client folder structure and shared workspace. | 2026-09-06 | Welcome email already sent.
CL-003 | Peakline Media | Agency | 2026-09-03 | 2026-09-07 | Urgent | Information | Waiting | Admin VA | Follow up for completed onboarding questionnaire. | 2026-09-05 | Client has not submitted questionnaire.
CL-004 | Oak & Ink | Service Business | 2026-09-04 | 2026-09-08 | Normal | Welcome | Completed | Admin VA | Confirm kickoff details. | 2026-09-06 | Initial onboarding complete.

## Onboarding Checklist
ONBOARDING CHECKLIST
Standardized task list for every new client
Step ID | Onboarding Step | Category | Owner | Status | Due / Target | Standard / Expected Result | Notes
STEP-01 | Receive signed agreement | Information | Admin VA | Completed | Day 0 | Agreement received and filed in client folder.
STEP-02 | Send onboarding questionnaire | Communication | Admin VA | Completed | Day 0 | Client receives clear instructions and deadline.
STEP-03 | Collect required documents | Documents | Admin VA | In Progress | Day 1–2 | All required documents received and checked.
STEP-04 | Create client folder structure | Files | Admin VA | Completed | Day 1 | Standard folders created and named consistently.
STEP-05 | Set up shared workspace | Setup | Admin VA | In Progress | Day 1–2 | Access and workspace settings confirmed.
STEP-06 | Send welcome / next steps email | Communication | Admin VA | Completed | Day 2 | Client receives expectations and next steps.
STEP-07 | Confirm kickoff details | Follow-up | Admin VA | Not Started | Day 2–3 | Meeting/date/time confirmed with client.
STEP-08 | Review onboarding completion | Follow-up | Admin VA | Not Started | Day 3–5 | All checklist items complete or documented as pending.

## Client Information
CLIENT INFORMATION SHEET
Example intake record for onboarding
Client ID | CL-001
Business Name | BrightPath Consulting
Client Type | Consultant
Primary Contact | Jordan Lee
Email | jordan@example.com
Preferred Contact | Email
Services Requested | Administrative support, documentation, workflow organization
Primary Goal | Create a more organized backend and reduce recurring admin workload
Communication Notes | Weekly check-in; urgent items flagged by email

## Document Checklist
DOCUMENT CHECKLIST
Track requested, received, and verified onboarding documents
Client ID | Document | Required? | Status | Requested Date | Received Date | Verified By | Notes
CL-001 | Signed Service Agreement | Yes | Received | 2026-09-01 | 2026-09-01 | Admin VA | Filed in Agreements folder.
CL-001 | Onboarding Questionnaire | Yes | Received | 2026-09-01 | 2026-09-02 | Admin VA | Reviewed for completeness.
CL-001 | Brand / Business Information | Yes | Received | 2026-09-01 | 2026-09-02 | Admin VA | Stored in Client Info folder.
CL-001 | Access / Platform Details | Yes | Requested | 2026-09-02 |  |  | Pending client response.
CL-001 | Reference Documents | No | Not Requested |  |  |  | Only if applicable.

## Email Templates
CLIENT ONBOARDING EMAIL TEMPLATES
Reusable communication examples for onboarding
1. Welcome Email | Subject: Welcome to the team — next steps | Hi [Client Name], Welcome! We're excited to get started. To complete your onboarding, please review the attached checklist and submit the requested information/documents by [Date]. Once everything is received, we'll confirm the next steps and kickoff details. Best, [Your Name]
2. Missing Documents | Subject: Quick follow-up — onboarding items | Hi [Client Name], Just a quick follow-up regarding the remaining onboarding items: [Items]. Whenever convenient, please send them by [Date] so we can keep your setup moving. Thank you, [Your Name]
3. Onboarding Complete | Subject: Your onboarding is complete | Hi [Client Name], Your onboarding is now complete. Your information and documents have been organized, and the next steps are ready. Our next scheduled action is [Next Step / Date]. Looking forward to working with you! Best, [Your Name]